## Slide 1
Ekurhuleni OPERATIONS REPORT
Ekurhuleni 25 August 2026 | Tuesday 25 august | 15:00
94
Valid cases
32/112
Wards covered
28.6%
Coverage
80
Wards missing
33
VOC ready / done
AMBER
Overall status
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00

## Slide 2
1. EXECUTIVE COVERAGE SNAPSHOT
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
Where we are now
94 valid cases on 25 August 2026; 12 new wards today; 32 wards reached cumulatively (28.6% of 112).
What changed
Today: 94 cases and 12 new wards. New wards are unique to the selected reporting date after checking all prior valid dates; running wards are cumulative unique wards.
What needs attention
80 ward allocations remain. To reach the 112-ward weekly target by Friday, aim for 27 new wards per remaining working day (3 days).
Cases on reporting date
Day
Cases
New wards
Running total
Still needed
2026-08-24
72
20
20/112
92
2026-08-25
94
12
32/112
80
—
—
—
—
—
—
—
—
—
—
Recommended focus
Validate ward representation (80 missing). Protect observed peak intake periods. Use the addendum for detailed evidence.
Chart: Reporting date
| 2026-08-24 | 2026-08-25
Cases | 72 | 94

## Slide 3
2. WARD COVERAGE BY MUNICIPALITY / REGION
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
Area
Target
Covered
Missing
%
NORTH EAST CORRIDOR
62
9
53
14.5%
SOUTH EAST CORRIDOR
50
10
40
20.0%
Total
112
19
93
17.0%
Validation
112
111
1
111 unique / 112 listed
Covered vs missing wards by area
Interpretation
Selected-day coverage: 19 of 112 listed ward allocations were covered across North East and South East. Cumulative progress remains 32/112; master validation: 111 unique ward numbers and 1 observed ward numbers outside the master.
Call-list link
The addendum contains the ward evidence and validation trail.
Chart: Area
| NORTH EAST CORRIDOR | SOUTH EAST CORRIDOR
Covered | 9 | 10
Missing | 53 | 40

## Slide 4
3. CHANNEL AND TIME COVERAGE
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
Channel
Cases
%
New wards
Quality note
Outbound Call
93
98.9%
11
Demand concentration
Inbound Call
1
1.1%
1
Monitor mix
0
0
0%
0
0
0
0
0%
0
0
Channel mix
Time coverage / hourly activity
What management should see
Observed window: 07:06–14:31. Peak: 13:00 (26 cases).
Chart: Channel
| Outbound Call | Inbound Call
Cases | 93 | 1
Chart: Hour of day
| 07:00 | 08:00 | 09:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00
Cases | 8 | 6 | 15 | 9 | 7 | 1 | 26 | 22

## Slide 5
4. SERVICES AND DEMAND MIX
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
Top services logged
Service / cluster
Cases
%
Comment
Roads Services
1,703
22.0%
Leading demand category
Electricity Services
1,090
14.1%
Demand indicator
Environment Services
1,079
13.9%
Demand indicator
Other
2,896
42.8%
Remaining categories
Message rule
Use demand concentration to target follow-up; do not interpret case volume as departmental performance.
Follow-up prompts
Use the addendum for low-volume services and ward-level detail.
Chart: Service category
| Roads Services | Electricity Services | Environment Services | Water Services | Sanitation Services
Count | 1703 | 1090 | 1079 | 577 | 334

## Slide 6
5. VOICE OF THE CITIZEN AND RESOLUTION POSITION
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
33
VOC responses
74.2%
Happiness
23
Resolved cases
31/33
Survey-ready
Available
Data availability
Case / queue
Ward
Service
Action
0
0
Not available
Call / verify / close
0
0
Not available
Call / verify / close
0
0
Not available
Call / verify / close
VOC reporting rule
VOC source supplied. Metrics are calculated only from supported response fields; detailed responses remain in the addendum.

## Slide 7
6. ACTIONS, DATA QUALITY AND MANAGEMENT DECISIONS
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 25 August 2026 | 15:00
Priority
Owner
Timing
Success check
Missing wards
Ops lead
Next close
80 wards validated/assigned
Channel/time gap
Supervisor
Next operating window
Peak hours protected
VOC queue
VOC lead
Current period
33 VOC responses reviewed
Data quality
Data lead
Before circulation
4 quality findings reviewed
Priority control load
Decision needed
Confirm and assign the 80 unrepresented wards before the next operational close.
Data caveat
Area-level municipality breakdown requires a validated ward/master reference mapping.
Addendum pointer
Detailed graphs, accounted wards, missing wards, time logs and correction registers are attached separately.
Chart: Control area
| Missing wards | Channel/time | VOC queue | Data quality
Count | 80 | 1 | 33 | 4