## Slide 1
Ekurhuleni OPERATIONS REPORT
Ekurhuleni 02 September 2026 | Wednesday 2 September | 15:00
104
Valid cases
24/112
Wards covered
21.4%
Coverage
88
Wards missing
18
VOC ready / done
AMBER
Overall status
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00

## Slide 2
1. EXECUTIVE COVERAGE SNAPSHOT
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
Where we are now
104 valid cases on 02 September 2026; 24 new wards today; 24 wards reached cumulatively (21.4% of 112).
What changed
Today: 104 cases and 24 new wards. New wards are unique to the selected reporting date after checking all prior valid dates; running wards are cumulative unique wards.
What needs attention
88 ward allocations remain. To reach the 112-ward weekly target by Friday, aim for 44 new wards per remaining working day (2 days).
Cases logged per hour
Day
Cases
New wards
Running total
Still needed
2026-09-02
104
24
24/112
88
—
—
—
—
—
—
—
—
—
—
—
—
—
—
—
Recommended focus
Validate ward representation (88 missing). Protect observed peak intake periods. Use the addendum for detailed evidence.
Chart: Hour of day
| 06:00 | 07:00 | 08:00 | 09:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00
Cases | 15 | 15 | 11 | 28 | 8 | 3 | 2 | 12 | 10

## Slide 3
2. WARD COVERAGE BY MUNICIPALITY / REGION
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
Area
Target
Covered
Missing
%
NORTH EAST CORRIDOR
62
15
47
24.2%
SOUTH EAST CORRIDOR
50
9
41
18.0%
Total
112
24
88
21.4%
Validation
112
111
0
111 unique / 112 listed
Covered vs missing wards by area
Interpretation
Selected-day coverage: 24 of 112 listed ward allocations were covered across North East and South East. Cumulative progress remains 24/112; master validation: 111 unique ward numbers and 0 observed ward numbers outside the master.
Call-list link
The addendum contains the ward evidence and validation trail.
Chart: Area
| NORTH EAST CORRIDOR | SOUTH EAST CORRIDOR
Covered | 15 | 9
Missing | 47 | 41

## Slide 4
3. CHANNEL AND TIME COVERAGE
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
Channel
Cases
%
New wards
Quality note
Outbound Call
104
100.0%
24
Demand concentration
0
0
0%
0
0
0
0
0%
0
0
0
0
0%
0
0
Channel mix
Time coverage / hourly activity
What management should see
Observed window: 06:26–14:29. Peak: 09:00 (28 cases).
Chart: Channel
| Outbound Call
Cases | 104
Chart: Hour of day
| 06:00 | 07:00 | 08:00 | 09:00 | 10:00 | 11:00 | 12:00 | 13:00 | 14:00
Cases | 15 | 15 | 11 | 28 | 8 | 3 | 2 | 12 | 10

## Slide 5
4. SERVICES AND DEMAND MIX
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
Top services logged
Service / cluster
Cases
%
Comment
Electricity Services
26
25.0%
Leading demand category
Roads Services
24
23.1%
Demand indicator
Environment Services
22
21.1%
Demand indicator
Other
32
30.8%
Remaining categories
Message rule
Use demand concentration to target follow-up; do not interpret case volume as departmental performance.
Follow-up prompts
Use the addendum for low-volume services and ward-level detail.
Chart: Service category
| Electricity Services | Roads Services | Environment Services | Water Services | Sanitation Services
Count | 26 | 24 | 22 | 17 | 9

## Slide 6
5. VOICE OF THE CITIZEN AND RESOLUTION POSITION
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
18
VOC responses
68.8%
Happiness
11
Resolved cases
16/18
Survey-ready
Available
Data availability
Case / queue
Ward
Service
Action
0
0
Not available
Call / verify / close
0
0
Not available
Call / verify / close
0
0
Not available
Call / verify / close
VOC reporting rule
VOC source supplied. Metrics are calculated only from supported response fields; detailed responses remain in the addendum.

## Slide 7
6. ACTIONS, DATA QUALITY AND MANAGEMENT DECISIONS
AMBER
Ekurhuleni | INTERNAL SDI OPERATIONS REPORTING | 02 September 2026 | 15:00
Priority
Owner
Timing
Success check
Missing wards
Ops lead
Next close
88 wards validated/assigned
Channel/time gap
Supervisor
Next operating window
Peak hours protected
VOC queue
VOC lead
Current period
18 VOC responses reviewed
Data quality
Data lead
Before circulation
0 quality findings reviewed
Priority control load
Decision needed
Confirm and assign the 88 unrepresented wards before the next operational close.
Data caveat
Area-level municipality breakdown requires a validated ward/master reference mapping.
Addendum pointer
Detailed graphs, accounted wards, missing wards, time logs and correction registers are attached separately.
Chart: Control area
| Missing wards | Channel/time | VOC queue | Data quality
Count | 88 | 1 | 18 | 0